## v2.1
WBS Level | Activity Name | Activity Description including deliverable | Owner Name + [FTE*] | Other resources needed | Specific competencies, skills, experience needed | Estimated Effort & Duration | Estimated Costs | Dependencies | Status
|  |  |  | Name+ [FTE*] |  |  |  | plus any true date constraints
1 | Project Management | Provide Project Management services to deliver MRMv2.1 | Jim Amsden [0.2] |  | Project Management | 7 days |  | Most activities done during the pilot project. | Pending
2 | Program Management | Overall program and client management | Alison Oleksiak | Bruce Baron [0.2] | Program Management | Ongoing |  |  | In Process
3 | Requirements Scoping | Continuous requirements elicitation and management as requirments evolve | Jim Amsden |  | Requirements Management | Continuous requirements management, 2 days |  |  | In Process
4 | MRM Knowledge Engineering | Capture and validate additional MRM content, especially connecting service outputs to outcomes, and their target groups and needs | Skip Lumley |  | MRM | By others, part of the MISA pilot projects |  | This may be sufficiently complete for the MISA pilot projects. Tehre may be an opportunity for follow-on knowledge engineering. | Out of Scope
4.1 | Inventory of MRM Reference Components | Determine what materials are available as data sources for additional MRM content | Skip Lumley, Roy Weisman |  | MRM | By others, part of the MISA pilot projects |  | Roy has provided hard-copy to Skip. Some spreadsheets may be able to be transformed into something that can be input into SA | Out of Scope
4.2 | Inventory of Best Practices Components |  | Skip Lumley |  | MRM | By others, part of the MISA pilot projects |  |  | Out of Scope
4.3 | Inventory of Municipality MRM Customizations |  | Skip Lumley |  | MRM | By others, part of the MISA pilot projects |  |  | Out of Scope
5 | Product Integrations | Develop required integrations between elements of the tooling architecture | Quickr Developer |  | Lotus Quickr, SA Publishing, SA/XT | covered in more specific sub-tasks |  | This should be simply links from Quickr to Web published data from SA Publisher and to SA/XT links. The time is for link organization. | In Process
5.1 | Lotus Quickr and Rational System Architect | Provide integration between models and reports published from SA, and access to live data from SA/XT from the Quickr MRM collaboration site. Create SA Publisher template to publish MRM models. | Pierre Bentkowski | Developer | Lotus Quickr, SA Publisher, SA reporting, SA/XT | 8d - due Dec 24 |  | Needs SA/XT implementation and development of SA Publisher template for MRM. Can use TeamSD SA Publisher template as an example. | Pending
6 | MRM Implementation | Develop the implementation of the MRM meta-model and reference model | Jim Amsden | Chuck Farris, Martin Owen (consulting) | SA Extensibility |  |  |  | Done
6.1 | MRM Meta-Model implementation | Implementation of the MRMv2 metamodel in SA USRPROPS.TXT | Jim Amsden | Chuck Farris | meta-modeling, SA extensibility | 6d |  | Metamodel updates from MISA review and definition dialog layouts. | Done
6.2 | MRM Reference Model migration | Migrate the MRM reference model from the current ReqPro repository to SA | Jim Amsden |  | CSV file processing, SA CSV import | 1d |  |  | Done
6.3 | Implement MRM Work Products | Implement the agreed-upon work products supporting MRM pilot projects, and alignment with PSRM where applicable. |  |  |  | covered in more specific sub-tasks |  |  | In Process
6.3.1 | Business Architecture Report | A report with selectable scope and depth to summarize the Organization Unit, Program, Service, Process, Resource model elements. | Pierre Bentkowski |  | SA reporting | 8d - Due Dec 3 |  | This is a complex report that will be one of the primary work products of an MRM engagement. | Pending
6.3.2 | Program Profile Report | A combination of the SA corresponding definition dialog and a summary report. | Jim Amsden |  | SA reporting | 1d |  |  | Pending
6.3.3 | Organization Unit Profile Report | A combination of the SA corresponding definition dialog and a summary report. | Pierre Bentkowski |  | SA reporting | 2d - Due Nov 12 |  | This is the first of the profile reports and will create longer. The others are similar and can be based on this one. | Pending
6.3.3 | Service Profile Report | A combination of the SA corresponding definition dialog and a summary report. | Jim Amsden |  | SA reporting | 1d |  |  | Pending
6.3.4 | Report and SA Publisher support | Provide support and possible updates to reports and MRM SA Publisher templates | Pierre Bentkowski |  |  | 2d
6.3.4 | SIAM Diagram | Service Integration and Accountability Diagram. Shows the relationship between organization units and the programs and services they provide to target groups. | Jim Amsden | Martin Owen (consultant) | SA Extensibility, Explorer diagram definitions and reports | 10d |  |  | Done
6.3.4 | Hierarchy Diagrams | SA 7 Hierarchy diagrams for all meta-classes that have hierarchies | Jim Amsden | Martin Owen (consultant) | SA Extensibility | 4d |  | Waiting on a defect for HierarchyBuilder macro update to 11.4 | In Process
6.3.5 | Relationship Matrices | Create a matrix for each relationship in the meta-model to support viewing, navigating and editing all relationships. | SA Developer |  | SA Extensibility | 6d |  | Additional matrices for the relationship definitions can be created when MRM updates to 11.4.0.1 (Dec 17) | Done
6.3.6 | MRM Browsers | Create 2 browsers organizing information specific MRM roles (Business User and Business Analyst) | SA Developer |  | SA Extensibility | 2d |  |  | Done
7 | MRM Web Site Implementaiton | Implement the Web Site used by MRM Business Users and Business Analysts |  |  | Lotus Quickr, SA Publishing | By others, part of the MISA pilot projects |  | This will be content that is created by the pilot project, perhaps mined from previous projects | Out of Scope
7.1 | Login/Registration Page | A page supporting business user and business analysts login, and registration for new users | Web Developer |  | Web 2.0, Lotus Quickr |  |  | Part of Quickr | Done
7.2 | Home Page | Provides an introduction to the municipality to the MRM and its use | Web Developer |  | Web 2.0, Lotus Quickr | By others, part of the MISA pilot projects |  | Part of Quickr | Out of Scope
7.3 | News Page | Provides a page of information about changes to the MRM and other related news | Web Developer |  | Web 2.0, Lotus Quickr | By others, part of the MISA pilot projects |  |  | Out of Scope
7.4 | MRM Access Page | Provides access to the MRM content, either published or live content through SA/XT | Web Developer |  | Web 2.0, Lotus Quickr | By others, part of the MISA pilot projects |  |  | Out of Scope
7.5 | MRM Discussion Forum | Provides a page for general discussion about the use of the MRM. | Web Developer |  | Web 2.0, Lotus Quickr | By others, part of the MISA pilot projects |  | Part of Quickr | Out of Scope
7.6 | MRM Reference Material Page | A page that provides a municipality with source documentation and reference material that can be downloaded in a variety of formats, and allows the MRM V2 custodian to add, delete and modify source / reference documents from time to time. | Web Developer |  | Web 2.0, Lotus Quickr | By others, part of the MISA pilot projects |  | I'm assuming all Quickr site content will be done by MISA in the pilot projects. | Out of Scope
7.7 | MRM Meta-model access page | A published version of the MRM meta-model for reference purposes | Web Developer |  | Web 2.0, Lotus Quickr | covered in more specific sub-tasks |  |  | In Process
7.8 | Change Requests Page | A page for entering change requests for the MRM itself, including defects and enhancements of the meta-model and/or reference model | Web Developer |  | Web 2.0, Lotus Quickr | By others, part of the MISA pilot projects |  | Depends on Quickr support, or the need to integrate something like Bugzilla. | Out of Scope
7.9 | Contacts Page | A page that identifies key stakeholders that may govern the MRM Software / Web Site, that may be accountable for providing MRM V2 services, and that may be key contacts for various reference models, including Customized Municipal Models. | Web Developer |  | Web 2.0, Lotus Quickr | By others, part of the MISA pilot projects |  | Contacts obtained from MISA | Out of Scope
7.1 | Help Page | A page that provides help / assistance to the MRM V2 Software users. This help will include MRM V2 Software feature help, as well as help about the business components, and uses. | Web Developer |  | Web 2.0, Lotus Quickr | 5d
8 | Documentation | User's Guide. | Skip Lumley |  | MRM | By others, part of the MISA pilot projects |  | Being done by MISA based on existing project requirements, desgn and functional documentation | Out of Scope
8.1 | On-Line Help | On-line help documentation guiding users through the use of the tooling in support of the key user stories. | ID Developer |  | Information Development | 3d |  | 8.2, 8.3, 8.4, 8.5
8.2 | Municipal Business User Guide | A document describing how Business Users use the tooling in support of their activities (a published version of the on-line help for SA tooling and the Help page) | ID Developer |  | Information Development | 5d |  | 8.4, 8.5
8.3 | Municipal Custodian Guide | A guide describing how a Business Analyst and Meta Modeler would modify the reference model and/or its describing meta-model. | ID Developer |  | Information Development | 5d |  | 8.4, 8.5
8.4 | Business Use Cases, Operations, Features and Specifications | Updated design documents formalizing the supported user stores and informing the help documents. | ID Developer |  | Information Development | 2d |  | Update existing document to new tool environment. 8.5 | Done
8.5 | Workbench Design Document | A document describing the overal design of the supported tooling. | ID Developer |  | Information Development | 2d |  |  | Pending
9 | Governance Process | A document describing the MISA governance process, and processes for collaborative lifecycle management of the MRM and its meta-model. | Jim Amsden |  | CLM, ITIL | 5d
10 | Knowledge Transfer, Training | [6 empty] | Part of pilot project support | Pending
10.1 | Deployment Environment Specification | A specification of the target deployment environment for the MISA pilot projects. | Developer |  | SA, Quickr, possibly RAM, RTC, Cognos, RPE | 3d
10.2 | Installation Instructions | A document describing the installation instructions for the MRM tooling. | ID Developer |  | Informaiton Development | 3d |  | 10.1 | In Process
10.3 | Configuration Instructions | A document describing the configuration instructions for the installed MRM tooling. | ID Developer |  | Informaiton Development | 3d |  | 10.1, 10.2 | In Process
10.4 | Backup and Recovery | A document describing the encyclopedia and web site content backup and recovery procedures. | ID Developer |  | Informaiton Development, SA Encyclopedia Manager | 1d |  | Augmenting SA Encyclopedia Manager documentation with MRM-specific details. | Pending
10.5 | Best Practices Mentoring | Providing best practices guidelines and services on tool usage and extensibility. | Jim Amsden |  | MRM, SA, Quickr | 10d |  | Part of pilot project suport | Pending
10.6 | Example scenario viewlets | Development of viewlets demonstrating each of the user stories. | Jim Amsden |  | MRM, SA, Quickr | 5d