## v2.1
WBS Level | Activity Name | Activity Description including deliverable | Owner Name + [FTE*] | Other resources needed | Specific competencies, skills, experience needed | Estimated Effort & Duration | Estimated Costs | Dependencies | Status
|  |  |  | Name+ [FTE*] |  |  |  | plus any true date constraints
1 | Project Management | Provide Project Management services to deliver MRMv2.1 | Jim Amsden [0.2] |  | Project Management | 7 days |  | Most activities done during the pilot project. | Pending
2 | Program Management | Overall program and client management | Alison Oleksiak | Bruce Baron [0.2] | Program Management | Ongoing |  |  | In Process
3 | Requirements Scoping | Continuous requirements elicitation and management as requirments evolve | Jim Amsden |  | Requirements Management | Continuous requirements management, 2 days |  |  | In Process
5 | Product Integrations | Develop required integrations between elements of the tooling architecture | Quickr Developer |  | Lotus Quickr, SA Publishing, SA/XT | covered in more specific sub-tasks |  | This should be simply links from Quickr to Web published data from SA Publisher and to SA/XT links. The time is for link organization. | In Process
5.1 | Rational System Archiecture web site | Create a SA Publisher template to generate a web site of the whole municipal model (too later be accessed by users throught the Quickr Site | Pierre Bentkowski | Pierre Bentkowski | SA Publisher | 10d |  | Needs SA/XT implementation and output from SA Publisher for MRM | Pending
5.2 | Rational System Archicture reports - RPE | Provide 4 SA Report templates to generate Words document - Organization, - Program, - Service Profile, and - Business Model report | Pierre Bentkowski | Pierre Bentkowski | SA and RPE | 15d |  | Needs SA/XT implementation and output from SA Publisher for MRM | Pending
5.3 | Rational System Archicture reports - SA Publisher | Provide a SA Report templates to generate Words document of the of the municipal model | Pierre Bentkowski | Pierre Bentkowski | SA Publisher | 3d |  | Needs SA/XT implementation and output from SA Publisher for MRM | Pending
5.? | Lotus Quickr and Rational System Archicture | Provide integration between models and reports published from SA, and access to live data from SA/XT from the Quickr MRM collaboration site |  |  | Lotus Quickr, SA model publish, SA reporting, SA/XT | 3d |  | Needs SA/XT implementation and output from SA Publisher for MRM | Pending
6.3 | Implement MRM Work Products | Implement the agreed-upon work products supporting MRM pilot projects, and alignment with PSRM where applicable. |  |  |  | covered in more specific sub-tasks |  |  | In Process
6.3.1 | Business Model Report | A report with selectable scope and depth to summarize the Organization Unit, Program, Service, Process, Resource model elements. | Developer |  | SA reporting | 5d |  |  | Pending
6.3.2 | Program Profile Report | A combination of the SA corresponding definition dialog and a summary report. | SA Developer |  | SA reporting | 3d |  |  | Pending
6.3.3 | Organization Unit Profile Report | A combination of the SA corresponding definition dialog and a summary report. | SA Developer |  | SA reporting | 3d |  |  | Pending
6.3.3 | Service Profile Report | A combination of the SA corresponding definition dialog and a summary report. | SA Developer |  | SA reporting | 3d |  |  | Pending
6.3.4 | Hierarchy Diagrams | SA 7 Hierarchy diagrams for all meta-classes that have hierarchies | Jim Amsden | Martin Owen (consultant) | SA Extensibility | 4d |  | Waiting on a defect for HierarchyBuilder macro update to 11.4 | In Process
7.1 | Login/Registration Page | A page supporting business user and business analysts login, and registration for new users | Web Developer |  | Web 2.0, Lotus Quickr |  |  | Part of Quickr | Done
7.7 | MRM Meta-model access page | A published version of the MRM meta-model for reference purposes | Web Developer |  | Web 2.0, Lotus Quickr | covered in more specific sub-tasks |  |  | In Process
7.1 | Help Page | A page that provides help / assistance to the MRM V2 Software users. This help will include MRM V2 Software feature help, as well as help about the business components, and uses. | Web Developer |  | Web 2.0, Lotus Quickr | 5d
8.1 | On-Line Help | On-line help documentation guiding users through the use of the tooling in support of the key user stories. | ID Developer |  | Information Development | 3d |  | 8.2, 8.3, 8.4, 8.5
8.2 | Municipal Business User Guide | A document describing how Business Users use the tooling in support of their activities (a published version of the on-line help for SA tooling and the Help page) | ID Developer |  | Information Development | 5d |  | 8.4, 8.5
8.3 | Municipal Custodian Guide | A guide describing how a Business Analyst and Meta Modeler would modify the reference model and/or its describing meta-model. | ID Developer |  | Information Development | 5d |  | 8.4, 8.5
8.5 | Workbench Design Document | A document describing the overal design of the supported tooling. | ID Developer |  | Information Development | 2d |  |  | Pending
9 | Governance Process | A document describing the MISA governance process, and processes for collaborative lifecycle management of the MRM and its meta-model. | Jim Amsden |  | CLM, ITIL | 5d
10 | Knowledge Transfer, Training | [6 empty] | Part of pilot project support | Pending
10.1 | Deployment Environment Specification | A specification of the target deployment environment for the MISA pilot projects. | Developer |  | SA, Quickr, possibly RAM, RTC, Cognos, RPE | 3d
10.2 | Installation Instructions | A document describing the installation instructions for the MRM tooling. | ID Developer |  | Informaiton Development | 3d |  | 10.1 | In Process
10.3 | Configuration Instructions | A document describing the configuration instructions for the installed MRM tooling. | ID Developer |  | Informaiton Development | 3d |  | 10.1, 10.2 | In Process
10.4 | Backup and Recovery | A document describing the encyclopedia and web site content backup and recovery procedures. | ID Developer |  | Informaiton Development, SA Encyclopedia Manager | 1d |  | Augmenting SA Encyclopedia Manager documentation with MRM-specific details. | Pending
10.5 | Best Practices Mentoring | Providing best practices guidelines and services on tool usage and extensibility. | Jim Amsden |  | MRM, SA, Quickr | 10d |  | Part of pilot project suport | Pending
10.6 | Example scenario viewlets | Development of viewlets demonstrating each of the user stories. | Jim Amsden |  | MRM, SA, Quickr | 5d